## Sheet1
Task | Hours | Done
Update import process to include new yearly tables used to speed up dashboard. | 0
Add a context menu to detector page Experience: design Experience: ux Priority: low This issue can probably be picked up by anyone looking to contribute to the project, as an entry fixType: feature@vwolfley | 4 | 4
Ability to export Generated Report to excel Experience | 6 | 6
In Report History have ability to delete generated report Experience | 4 | 4
Chart - Distribution of Data Passing Quality Control Criteria by Date | 8 | 8
Chart - Distribution of Data Passing Quality Control Criteria by Weekday | 8 | 8
Chart - Annual Quality Control Flags by Hour of Day - weekdays | 8 | 8
Chart - Flow vs Density - All data rows & 5-min Weekday Average | 0
Chart - Speed vs Density - All data rows & 5-min Weekday Average | 0
Chart - Speed vs Flow - All data rows & 5-min Weekday Average | 0
Table - Count of Quality Control Flags by Time Period - Weekdays | 4 | 2
Table - Percent of Data Rows Flagged by Time Period - Weekdays | 4 | 2
Reports History - Add Filter or search ability | 4
Reports History - Add processing time field | 1 | 1
Report History - Check data validation prior to submittal | 6
Report History - Fix ability to choose analysis for report | 4 | 4
Add ability to export to PDF | 0
Add email for when submitted report is done to user | 2 | 2
Rename the database from JacobsPlaypen | 1 | 1
Add Time of Day data to Database | 2 | 2
Fix main popup on home map | 2 | 2
Rename Home Link to Detectors | 1 | 1
Add ability to search for cached detector on detector page | 3 | 3
Total
Total Hours Estimate | 14 | 58
Hours per day | 6
Days to finish | 2.3333
Estimated Finish Date | 2023-04-21 |  | 2023-02-03
Formulas:
Hours = WORKDAY(TODAY(),[Hours, row above])